## Sheet1
Datum | Aktivität
2012-06-14 | Ausgabe des Themenkatalogs, Gespräch mit Dobler
2012-07-05 | Benachrichtigung über Genehmigung des Themas
2012-07-22 | Latex einrichten und Bachelorarbeitsvorlage von Burger downloaden
2012-07-23 | Anlegen SVN und Verzeichnisstruktur, Create project sort, Implement test for own quicksort, c qsort and c++ sort
2012-07-29 | Created OpenCL classes, Implemented Bealto ParallelSelectionSort
2012-07-31 | Implemented Bealto ParallelSelectionSortLocal and ParallelSelectionSortBlocks
2012-08-01 | Implemented Bealto ParallelBitonicSortLocal
2012-08-02 | Implemented Bealto ParallelBitonicSortA, ParallelBitonicSortB2 (first algorithm running faster than CPU Quicksort in Debug mode), ParallelBitonicSortB4 (first algorithm running faster than CPU Quicksort in Release mode)
2012-08-03 | Implemented ParallelBitonicSortB8, ParallelBitonicSortB16
2012-08-04 | Implemented Bealto ParallelBitonicSortC, ParallelMergeSort
2012-08-05 | Implemented LibCL RadixSort, Added some keywords to lexer file, Refactored RUN macros in main
2012-08-08 | Tried to get OpenSSL custom OpenCL engine running
2012-08-12 | Implemented AMD BitonicSort and RadixSort, Got an CPU AES Implementation running
2015-08-12 | Implemented clpp radix sort (not working), Implemented CPU Scan
2012-09-03 | Refactoring, Added Runner class
2012-09-05 | All Sorts working now, Adapted Scan project to new Runner architecture, deleted crypt project
2012-09-06 | Added NaiveScan and WorkEfficientScan from Gpu gems 3
2012-09-10 | Added LocalScan from Gpu gems 3
2012-09-11 | Further working on LocalScan
2012-09-12 | LocalScan technically working now, allocation problems with sizes > 2MiB
2012-09-14 | Fixed an issue in the OpenCL device information query methods, LocalScan works now up to 64M elements (256MiB)